## Aug 30 2017
Minutes of the Meeting
Project/Function Name | Ace designers PLM shared support | Project Id | 4193
Project Stage | Steady State Support | Meeting Date | 2017-12-21
Meeting Chairperson | Dibya Ranjan Mohanty | Role | Support Consultant
Minutes prepared by | Dibya Ranjan Mohanty | Next Meeting Date
Invitee present |  | Invitee Not Present
Rajendra H A
Ranjan M Asangi
Vadiraj Mysore
Ajith Kumar
Dibya Ranjan Mohanty
Meeting Agenda | Quarterly Governance Meeting
Minutes circulated to | All Stakeholders
Sl No | Action Items |  | Status | Ownership | Remarks
Sl No | Discussion points |  | Remarks
1 | To distribute a .bat file which can be used by users on-demand to delete their cache folder (.wf) |  | ITC Infotech will send the .bat file
2 | To check whether audit logs are getting generated for delete event. |  | ITC Infotech will check the audit logs and prepare a SOP for users to check the same.
3 | PTC Product Calendar to be shared with Ajith Sir and Vadiraj Sir |  | PTC Product Calendar was downloaded to the desktop of the computer in conference room.
4 | Creo Parametric improvement points to be shared with Ajith Sir and Vadiraj Sir |  | ITC Infotech will share the same.
5 | To enforce check-out of associated drawings if a CAD part or CAD assembly is getting checked-out |  | ITC Infotech will check its feasibility
6 | To find out if the .frm file information can be derived from the drawing |  | ITC Infotech will check its feasibility
7 | To pass the size of the drawing sheet as attribute |  | ITC will implement it in Test and inform to Ajith Sir
8 | To node-lock the Creo Parametric license to the systems of critical users |  | ACE Designers to decide and inform ITC Infotech
9 | To check the time-out for Creo Parametric license availability |  | ITC Infotech will check and inform
10 | To check if instead of watermark, pdf or pvz can be digitally signed |  | ITC Infotech will check and inform
11 | To check if representations can be moved to a separate vault through new vaulting rules so that physical location access control can be implemented by ACE Designers |  | ITC Infotech will check the feasibility of revaulting.
12 | Windchill Architechture explanation to Ranjan Sir |  | Provided
13 | To provide the active users list (from WinDU and DB) |  | ITC Infotech will provide.
2 | Topics with action points
Sl No | Action Items |  | Responsibility | Targeted closure date | Remarks | Status | Actual closure date
1 | To distribute a .bat file which can be used by users on-demand to delete their cache folder (.wf) |  | ITC Infotech | 2017-12-27 |  | Open
2 | To check whether audit logs are getting generated for delete event. |  | ITC Infotech | 2017-12-22 |  | Open
3 | Creo Parametric improvement points to be shared with Ajith Sir and Vadiraj Sir |  | ITC Infotech | 2017-12-26 |  | Open
4 | To enforce check-out of associated drawings if a CAD part or CAD assembly is getting checked-out |  | ITC Infotech | TBD |  | Open
5 | To find out if the .frm file information can be derived from the drawing |  | ITC Infotech | TBD |  | Open
6 | To pass the size of the drawing sheet as attribute (first on Test) |  | ITC Infotech | 2017-12-27 |  | Open
7 | To node-lock the Creo Parametric license to the systems of critical users |  | ACE Designers | TBD |  | Open
8 | To check the time-out for Creo Parametric license availability |  | ITC Infotech | 2017-12-22 |  | Open
9 | To check if instead of watermark, pdf or pvz can be digitally signed |  | ITC Infotech | TBD |  | Open
10 | To check if representations can be moved to a separate vault through new vaulting rules so that physical location access control can be implemented by ACE Designers |  | ITC Infotech | TBD |  | Open
11 | To provide the active users list (from WinDU and DB) |  | ITC Infotech | 2017-12-22 |  | Open